## Guidance Notes
Stakeholder Analysis
Why Complete a Stakeholder Analysis?
Identifying stakeholders upfront ensures you capture everyone involved or impacted by the change
Analysis helps build a Change Management Plan by identifying those who need to be involved
The analysis will help build a Change Communications Plan by identifying those who need to be communicated to through the change
The analysis will help understand which stakeholders to prioritise based on their level of interest and influence in the project
Failure to complete a Stakeholder Analysis may result in missing essential audiences required to support the change
Stakeholder Types
Internal Stakeholders may include (depending on the size of your firm):
CEO, COO, CIO, Functional Leads, Impacted Team Leaders, Non-Impacted Team Leaders, Impacted Employees/End Users, Non-impacted Employees, HR, Legal, Finance
External Stakeholders may include (depending on the type of market firm):
Brokers, carriers, DAs (Coverholders/TPAs etc.), Vendors, Regulators, Carriers
Guidance for use:
Brainstorm which stakeholders are connected to Blueprint Two in you organisation. Some examples are provided above.
Complete the Stakeholder Tool worksheet in this document with their group (e.g. Claims/Back office/Underwriting etc) or specific stakeholder name, role and business function.
(The Blueprint Two Playbook will help inform you of the solutions and therefore who may be impacted by any changes)
Consider what you need from each stakeholder or stakeholder group (project sponsorship, budget or resource allocation, understanding current processes, to be trained on new systems etc)
Consider the level of interest that you will need from them whether that's high, medium or low
Consider where the current level of interest is and whether that needs to be increased to match what's required by the project
Consider the stakeholders level of influence
Use the level of interest required and view of their level of influence to map them to the Power & Interest map to confirm which stakeholder strategy to use (e.g. Keep Satisfied, Manage Closely, Keep Informed or Monitor)
Consider what the stakeholder or stakeholder group will need to know and how best to provide workshops or updates
Consider the frequency of communication based on the stakeholder strategy
Consider the best way to communicate with the stakeholder or stakeholder group. What forms of communication will work best for them? Workshops, meetings, update emails, briefings, intranet site etc
Ensure each stakeholder or stakeholder group has a clear owner that is responsible for engagement and communication
Decide when communication and engagement should start with each stakeholder or stakeholder group

## Stakeholder Tool
Stakeholder Analysis Matrix
Project: |  |  | PLEASE NOTE: All dates and data shown are provided as an example only. Please update with real data and dates for the change
Completed By:
To be completed with Change Management and Comms
STAKEHOLDER GROUP | STAKEHOLDER NAME | ROLE / TITLE | BUSINESS FUNCTION | WHAT THE PROJECT NEEDS FROM THIS STAKEHOLDER | REQUIRED INTEREST LEVEL | ACTUAL INTEREST LEVEL | POWER / INFLUENCE | STAKEHOLDER MANAGEMENT STRATEGY | COMMUNICATION REQUIREMENTS | COMMUNICATION FREQUENCY | COMMUNICATION METHOD | STAKEHOLDER OWNER | COMMUNICATION START DATE
Internal
Exec | Name | CEO | Office of CEO | Buy in and approval | High | High | High | Manage Closely | Updates | Monthly | Meeting | Name | Feb 2023
Claims | Various | Claims team 1 | Claims | Use ICOS and EBOT | High | High | Medium | Manage Closely | Updates and Training | Include in readiness plan | Update sessions and training | Name | Q4 2023
External
Note on B5: Stakeholders could be groups of firms or people, or a specific firm or person depending on the type of change and impact.
Note on F5: What do we need from this stakeholder (e.g. awareness, business sponsorship, communication champion, buy in etc.
Note on G5: What level of interest do we need from this stakeholder to make the project a success (H/M/L)?
Note on H5: What is their current level of interest in the project (H/M/L) and does that match the interest level required? If no, then how can it be aligned? This field is RAG rated: Low = Red Medium = Amber High = Green
Note on I5: Degree of power and influence the stakeholder has on decision making within the Programme (H/M/L)
Note on J5: Use the Power & Interest Map to identifiy the strategy that can be used to most effectively work with this stakeholder. E.g. Manage Closely or simply Monitor
Note on K5: Understand their communication requirements for this project in terms of level of detail, frequency etc
Note on L5: Decide on the frequency of communication - weekly/monthly
Note on M5: Include the type of communication you will use for this stakeholdler e.g. meetings, newsletter, intranet, governance meetings etc. Consider format i.e. face to face, virtual or hybrid
Note on N5: Decide who is responsible for this stakeholer and the strategy employed to keep them engaged
Note on O5: Add the date that you intend to start communication with this stakeholder

## Power & Interest Map
Power & Influence Map
The Stakeholder map is used to identify the relative Power and Interest of each stakeholder and understand whose support you need, where you need to apply more time/effort in updating and what you need to move a Stakeholder from one part of the grid to another.
Stakeholder Power / Interest Grid
Keep Satisfied
Manage Closely
Monitor
Inform Regularly
Power / Influence
Interest
Low
High
Low
High

## Ref Data
Interest
High | Significant interest in the change being delivered
Medium | Some interest in the change being delivered
Low | Little or no interest in the change being delivered
Influence
High | Significant power to impact decisions, timescales or outcomes
Medium | Significant interest but less ability to influence project outcomes
Low | Little or no ability to change project outcomes
Stakeholder Strategy
Manage Closely | Personal engagement
Inform Reguarly | Keep informed proactively
Keep Satisfied | Provide updates and seek feedback
Monitor | Assess perceptions and react accordingly