## Guidance Notes
Change Impact Analysis
Why Complete an Change Impact Analysis for BP2?
Understand the scale of the change in terms of the number of employees impacted by the change
Understand the type of change based around people/behavioural, process, technology change and what activities are best suited to support people through the change
The analysis will help understand which impacted stakeholders are supportive or resistant to the change to help build plans to gain support
The analysis helps feed into a Change Management Plan based on the scale, current level or support and change activities required
Failure to complete a Change Impact Analysis may result in missing essential activities required to support the change
Guidance for use:
Use your stakeholder analysis to identify those who are impacted by the change and plot them to the Change Impact Analysis grid. Example text has been added in italics
Be clear on what's changing for each group. The Blueprint Two Playbook will help inform you of the solutions and likely impact
Consider whether the change relates to how people think or act, the processes they follow or the technology they use and therefore the type of change support that may be needed. In some cases it may be a combination of all three
Consider how you can involve the impacted stakeholders in the change. Can they participate in workshops, do you need 121s to fully understand the impact on them, do they need training, could they act as advocates to their peers etc
Consider how supportive the impacted stakeholders are of the change based on their satisfaction the with the current situation and their perceived benefits of the change
(Where they are happy with the current situation, more work will be required to rationalise the reason for the change and, where benefits are perceived as low, improved understanding or rationale will be required)
Consider whether impacted stakeholders are where you need them to be in terms of support. If not, how can you move them to supportive or champions. Not everyone may support the change, but it's important that the majority do
Consider the impacted stakeholders change capability. Do they understand their role in the change, what needs to change and what's expected of them to support the change?
Consider when the change will be delivered and check that aligns with the stakeholders view of being ready for the change. If there is a difference it's important to understand why and whether the timings need to align
By assessing the level of impact on the stakeholder, you can prioritise focus on those impacted the most as a starting point, although even those with a low impact may need some support
Add in the change activities that you have identified, when these need to be delivered by and by whom. These may include workshops, information sessions, process mapping and documentation, training plan, comms plan etc
Use your findings to help build out your change plan

## Change Impact Analysis
Detailed Impact Analysis
Project: |  |  | PLEASE NOTE: All dates and data shown are provided as an example only. Please update with real data and dates for the change
Completed By:
To be reviewed with Change Management & Comms
Impacted Stakeholder Group | No of people impacted | Description of the change | Type of Change Impact (People / Process / Technology) | Optional or Mandatory Change | How are they involved in creating the change | Dissatisfaction with current solution | Attractiveness of new solution | Desired level of support for the change | Actual support for change | Change capability | Date deliverable / change is ready for adoption by stakeholder | Date at which the deliverable / change is going to be adopted by stakeholder | Impact of change on stakeholder | Change activity | Owner | Due Date
Claims team | 11 - 50 | New claims process being introduced | Technology | Mandatory | Working groups | Open to enhancements | No benefits defined | Champion | Supportive | Strong | Q3 2024 | Q3 2024 | Medium | Update process guide | Allen | Q2 2023
[14 empty] | Grant users access | Gail | Q1 2024
[14 empty] | Produce training module | Susan | Q1 2024
[14 empty] | Deliver training | Susan | Q2 2024
[14 empty] | Dry run | Allen | Q3 2024
Notes are provided against each heading to aid completion
Note on B5: Stakeholder analysis template should be used as reference to populate this list, you may need use this at a different granularity
Note on C5: This will help decide on how to engage the stakeholder or group based on numbers
Note on D5: Summarise what the change means for this group. What do we need them to do differently for the change to be successful.
Note on E5: This is based on People, Process or Technology. You may need additional rows for the same stakeholder if change significantly impacts more than one area
Note on F5: Most change is mandatory but of optional a less formal approach may be suitable
Note on G5: This will help establish how you work with the stakeholder in creating the change
Note on H5: The aim to establish how open or resistant to the change the stakeholder is
Note on I5: The aim is to establish how well the stakeholder understands the benefits of the change to see if more work is required to gain buy in
Note on J5: What is the desired level of support needed from this stakeholder? Some stakeholders may make good champions or advocates of the change, so highlight these individuals and request their support.
Note on K5: Bruce, Allen: What is their current level of support for the change. If lower than desired level, consider how this can be improved
Note on L5: The aim is to understand the stakeholders' level of change capability and therefore the level of support they may need.
Note on M5: When are you targeting the change to be live e.g. Q3 2023 or Sep 2023
Note on N5: This should be the same as the delivery date, but highlights where a stakeholder does not envisage being ready in time
Note on O5: Is this change going to have a high, medium or low impact on the stakeholder. The higher the impact the more preparation and support will be required
Note on P5: These activities can feed into your change plan covering guidance notes, training, communications, information sessions etc)
Note on Q5: Each activity must have an owner who is responsible for actioning it by the due date
Note on R5: Include a date by with the change activity needs to be completed by. This can feed into your change plan

## Ref Data
Number of people affected | Notes / explanation | Adoption Priority | Anticipated change go live
1 - 10
11 - 50
51 - 100
100+
Primary change impact | Stakeholder(s) will experience an…
People/Behavioural | Impact on how people should do things
Process | Impact on how the process is carried out
Technology | Impact on technology used to do the job
Team structure | Impact on the structure of teams
Change type | Stakeholder(s) will…
Optional | Have a choice on implementing the change
Mandatory | The change must be adopted
Involvement in change | Stakeholder(s) were involved in...
Governance | The governance process, e.g. Steer Co
Working groups | Working groups contributing to proposals
Contributor | Contributions via other routes, e.g. 1:1 interview
Training required | Training
Other | Specify in the plan
No involvement | No involvement id defining the change
Dissatisfaction with current solution | Stakeholder(s) opinion of the current solution is…
Dissatisfied with current solution | Current solution does not meet stakeholder(s) needs
Open to enhancements | Current solution somewhat meets needs but could be made more efficient
Indifferent | No opinion of current solution
Satisfied with current solution | Current solution meets needs
Attractiveness of new solution | Stakeholder(s) view of the new solution is…
Benefits clearly articulated and understood | Benefits are clearly articulated and realisable
Recognise some benefits | There are some benefits which are realisable
No benefits defined | Benefits are yet to be assessed
No benefits identified | There are no realisable benefits
Change capability | Stakeholder(s) change capability is…
Strong | Understands change and how to make it successful
Medium | Understand the need for change but needs help
Low | Doesn't understand how change works
How supportive are you of the change? | Stakeholder(s) are…
Champion | Supporting the change and promoting it to their peers
Supportive | Supporting the change within their organisation and when dealing with Lloyd's
Neutral / indifferent | Indifferent to the change
Resistant | Resisting the change and would prefer it to go away
Change Impact | The impact of the change on the stakeholder(s) is…
High | High - will cause significant disruption and / or require a lot of resource to implement
Medium | Medium - will cause some disruption and / or require resource to implement
Low | Low - minimal disruption and / or little to no resource required to implement